## Overview
Projektnummer:
[8 empty] | Projektnamn: | ProgEx T2T Transfer
Sheet | Impl. PLC | Impl. HMI | Activation | Man mode | Alarm | Feedback | IO Check
Valves | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Motors | 0% | 0% | 0% | 0% | 0% | 0% | 0%
DI | 0% | 0% |  | 0% |  |  | 0%
DO | 0% | 0% |  | 0% |  |  | 0%
AI | 0% | 0% |  | 0% | 0% |  | 0%
AO | 0% | 0% | 0% | 0% |  |  | 0%
PID | 0% | 0% | 0% | 0%
Alarm | N/A | N/A
Revision
V1.1 | Added combobox to Valves, to be used in generator
V1.2 | Add EngUnit to AI

## Valve
|  |  | (InTouch) | (InTouch)
Drawing | ID | Description | Alarm Group | PLC | Impl. PLC | Impl. HMI | Activation | Man mode | Alarm | Feedback | IO Check | Responsible | Delay seconds
| 45 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | ON | OFF
| TL0T01V10 | Tank CIP pressure | TankToTank | PLC1
| TL0T01V01 | Tank Bottom Valve | TankToTank | PLC1
| TL0T01V02 | Tank Drain Valve | TankToTank | PLC1
| TL0T02V10 | Tank CIP pressure | TankToTank | PLC1
| TL0T02V01 | Tank Bottom Valve | TankToTank | PLC1
| TL0T02V02 | Tank Drain Valve | TankToTank | PLC1
| TL0L01V01 | Line Transfer TL0T01 | TankToTank | PLC1
| TL0L01V02 | Line Transfer TL0T02 | TankToTank | PLC1
| A50T01V10 | Tank CIP pressure | TankToTank | PLC1
| A50T01V01 | Tank Bottom Valve | TankToTank | PLC1
| A50T01V02 | Tank Drain Valve | TankToTank | PLC1
| A50T02V10 | Tank CIP pressure | TankToTank | PLC1
| A50T02V01 | Tank Bottom Valve | TankToTank | PLC1
| A50T02V02 | Tank Drain Valve | TankToTank | PLC1
| A50L01V03 | Line Transfer A50T01 | TankToTank | PLC1
| A50L01V04 | Line Transfer A50T02 | TankToTank | PLC1
| A30T01V10 | Tank CIP pressure | TankToTank | PLC1
| A30T01V01 | Tank Bottom Valve | TankToTank | PLC1
| A30T01V02 | Tank Drain Valve | TankToTank | PLC1
| TL0L02V01 | Line Transfer TL0T01 | TankToTank | PLC1
| TL0L02V02 | Line Transfer TL0T02 | TankToTank | PLC1
| T1600_V1000 | Drain | CIP | PLC2
| T1600_V1001 | Outlet L1600 | CIP | PLC2
| T1600_V1005 | Water | CIP | PLC2
| T1601_V1000 | Drain | CIP | PLC2
| T1601_V1001 | Outlet L1600 | CIP | PLC2
| T1601_V1003 | Inlet L1600 | CIP | PLC2
| T1601_V1004 | Inlet L1601 | CIP | PLC2
| T1602_V1000 | Drain | CIP | PLC2
| T1602_V1001 | Outlet L1600 | CIP | PLC2
| T1602_V1003 | Inlet L1600 | CIP | PLC2
| T1602_V1005 | Water | CIP | PLC2
| T1602_V1006 | Steam | CIP | PLC2
| T1602_V1007 | Concentration | CIP | PLC2
| T1603_V1000 | Drain | CIP | PLC2
| T1603_V1001 | Outlet L1600 | CIP | PLC2
| T1603_V1003 | Inlet L1600 | CIP | PLC2
| T1603_V1005 | Water | CIP | PLC2
| T1603_V1006 | Steam | CIP | PLC2
| T1603_V1007 | Concentration | CIP | PLC2
| L1601_V1100 | Steam | CIP | PLC2
| L1601_V1101 | BTD Inlet | CIP | PLC2
| L1601_V1102 | BTD Outlet | CIP | PLC2
| L1601_V1103 | BTD Drain | CIP | PLC2
| L1601_V1104 | End Line Drain | CIP | PLC2
Note on B3: Valve number from P&ID
Note on C3: Process description of the function of the valve
Note on E3: What PLC is the output controlled from?
Note on F3: Is the valve object implemented in the PLC program? X = Done P = In Progress
Note on G3: Is the valve object fully implemented on the HMI? X = Done P = In Progress
Note on H3: Is the activation tested? X = Done P = In Progress
Note on I3: Verify that you can put the valve in manual mode on the HMI. Check if correct PLC data was changed X = Done P = In Progress
Note on J3: Check that the valve is indicating Alarm state on the HMI and that an alarm in the alarm list is generated. X = Done P = In Progress
Note on K3: Is the correct feedback received from the Valve? Same as "IO check" X = Done P = In Progress
Note on L3: Is the valve fully IO tested? Meaning all inputs and outputs of the Valve are ok. X = Done P = In Progress
Note on N3: Are any activation / deactivation delays configured?

## Motor
|  |  | (InTouch) | (InTouch)
Drawing | ID | Description | Alarm Group | PLC | Impl. PLC | Impl. HMI | Activation | Man mode | Alarm | Feedback | IO Check | Responsible | Delay seconds
| 9 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | ON | OFF
| TL0T01M01 | Tank agitator | TankToTank | PLC1
| TL0T02M01 | Tank agitator | TankToTank | PLC1
| TL0L01M01 | Line pump | TankToTank | PLC1
| A50T01M01 | Tank agitator | TankToTank | PLC1
| A50T02M01 | Tank agitator | TankToTank | PLC1
| A30T01M01 | Tank agitator | TankToTank | PLC1
| T1602_M1000 |  | CIP | PLC2
| T1603_M1000 |  | CIP | PLC2
| L1601_M1101 |  | CIP | PLC2
Note on B3: Valve number from P&ID

## DI
|  |  | (InTouch) | (InTouch)
Drawing | ID | Description | Alarm Group | PLC | Impl. PLC | Impl. HMI | Man mode | Feedback | IO Check | Responsible | Delay seconds
| 15 |  |  |  | 0 | 0 | 0 | 0 | 0
[5 empty] | 0% | 0% | 0% | 0% | 0% |  | ON | OFF
| TL0T01LSH01 | Tank High Level | TankToTank | PLC1
| TL0T01LSL01 | Tank Low Level | TankToTank | PLC1
| TL0T01GS01 | Tank Manway | TankToTank | PLC1
| TL0T02LSH01 | Tank High Level | TankToTank | PLC1
| TL0T02LSL01 | Tank Low Level | TankToTank | PLC1
| TL0T02GS01 | Tank Manway | TankToTank | PLC1
| A50T01LSH01 | Tank High Level | TankToTank | PLC1
| A50T01LSL01 | Tank Low Level | TankToTank | PLC1
| A50T01GS01 | Tank Manway | TankToTank | PLC1
| A50T02LSH01 | Tank High Level | TankToTank | PLC1
| A50T02LSL01 | Tank Low Level | TankToTank | PLC1
| A50T02GS01 | Tank Manway | TankToTank | PLC1
| A30T01LSH01 | Tank High Level | TankToTank | PLC1
| A30T01LSL01 | Tank Low Level | TankToTank | PLC1
| A30T01GS01 | Tank Manway | TankToTank | PLC1
Note on B3: Valve number from P&ID

## DO
|  |  | (InTouch) | (InTouch)
Drawing | ID | Description | Alarm Group | PLC | Impl. PLC | Impl. HMI | Man mode | Alarm | Feedback | IO Check | Responsible | Delay seconds
| 1 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0% | 0% | 0% | 0% | 0% | 0% |  | ON | OFF
| ErrorLamp | Error lamp | TankToTank | PLC1
Note on B3: Valve number from P&ID

## AI
|  |  | (InTouch) | (InTouch) | [6 empty] | (InTouch) | (InTouch) | (InTouch)
Drawing | ID | Description | Alarm Group | PLC | Impl. PLC | Impl. HMI | Man mode | Alarm | IO Check | Responsible | Eng. Unit | Eng. Min | Eng. Max
| 36 |  |  |  | 0 | 0 | 0 | 0 | 0
[5 empty] | 0% | 0% | 0% | 0% | 0% |  |  | Min | Max
| TL0T01TT01 | Tank temperature | TankToTank | PLC1 | [6 empty] | °C | 0 | 160
| TL0T01PT01 | Tank bottom pressure | TankToTank | PLC1 | [6 empty] | bar | 0 | 10
| TL0T02TT01 | Tank temperature | TankToTank | PLC1 | [6 empty] | °C | 0 | 160
| TL0T02PT01 | Tank bottom pressure | TankToTank | PLC1 | [6 empty] | bar | 0 | 10
| A50T01TT01 | Tank temperature | TankToTank | PLC1 | [6 empty] | °C | 0 | 160
| A50T01PT01 | Tank bottom pressure | TankToTank | PLC1 | [6 empty] | bar | 0 | 10
| A50T02TT01 | Tank temperature | TankToTank | PLC1 | [6 empty] | °C | 0 | 160
| A50T02PT01 | Tank bottom pressure | TankToTank | PLC1 | [6 empty] | bar | 0 | 10
| TL0L01FT01 | Transfer line flow | TankToTank | PLC1 | [6 empty] | l/h | 0 | 50000
| TL0L01PT01 | Transfer line pressure | TankToTank | PLC1 | [6 empty] | bar | 0 | 10
| TL0T01LT01 | Tank Level | TankToTank | PLC1 | [6 empty] | % | 0 | 100
| TL0T02LT01 | Tank Level | TankToTank | PLC1 | [6 empty] | % | 0 | 100
| A50T01LT01 | Tank Level | TankToTank | PLC1 | [6 empty] | % | 0 | 100
| A50T02LT01 | Tank Level | TankToTank | PLC1 | [6 empty] | % | 0 | 100
| A30T01LT01 | Tank Level | TankToTank | PLC1 | [6 empty] | % | 0 | 100
| A30T01TT01 | Tank temperature | TankToTank | PLC1 | [6 empty] | °C | 0 | 160
| A30T01PT01 | Tank bottom pressure | TankToTank | PLC1 | [6 empty] | bar | 0 | 10
| TL0L02FT01 | Transfer line flow | TankToTank | PLC1 | [6 empty] | l/h | 0 | 50000
| TL0L02PT01 | Transfer line pressure | TankToTank | PLC1 | [6 empty] | bar | 0 | 10
| T1600_LT1000 |  | CIP | PLC2 | [6 empty] | l | 0 | 30000
| T1600_TT1001 |  | CIP | PLC2 | [6 empty] | °C | 0 | 160
| T1601_LT1000 |  | CIP | PLC2 | [6 empty] | l | 0 | 30000
| T1601_TT1001 |  | CIP | PLC2 | [6 empty] | °C | 0 | 160
| T1602_LT1000 |  | CIP | PLC2 | [6 empty] | l | 0 | 30000
| T1602_TT1001 |  | CIP | PLC2 | [6 empty] | °C | 0 | 160
| T1602_TT1002 |  | CIP | PLC2 | [6 empty] | °C | 0 | 160
| T1602_CT1003 |  | CIP | PLC2 | [6 empty] | mS | 0 | 200
| T1603_LT1000 |  | CIP | PLC2 | [6 empty] | l | 0 | 30000
| T1603_TT1001 |  | CIP | PLC2 | [6 empty] | °C | 0 | 160
| T1603_TT1002 |  | CIP | PLC2 | [6 empty] | °C | 0 | 160
| T1603_CT1003 |  | CIP | PLC2 | [6 empty] | mS | 0 | 200
| L1601_TT1100 |  | CIP | PLC2 | [6 empty] | °C | 0 | 160
| L1601_FT1101 |  | CIP | PLC2 | [6 empty] | l/h | 0 | 50000
| L1601_TT1102 |  | CIP | PLC2 | [6 empty] | °C | 0 | 160
| L1601_CT1103 |  | CIP | PLC2 | [6 empty] | mS | 0 | 200
| L1601_FT1104 |  | CIP | PLC2 | [6 empty] | l/h | 0 | 50000
Note on B3: Valve number from P&ID

## PID
|  |  | (InTouch) | (InTouch) | [8 empty] | (InTouch) | (InTouch) | (InTouch)
Drawing | ID | Description | Alarm Group | PLC | Impl. PLC | Impl. HMI | Activation | Man mode | Alarm | Feedback | Test | Responsible | Eng. Unit | Eng. Min | Eng. Max | Parameters
| 6 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  | Min | Max | P | I | D
| TL0L01FC01 | Flow controller | TankToTank | PLC1 | [8 empty] | l/h | 0 | 50000
| A50L01FC01 | Flow controller | TankToTank | PLC1 | [8 empty] | l/h | 0 | 50000
| L1601_FC1101 |  | CIP | PLC2 | [8 empty] | l/h | 0 | 50000
| L1601_TC1100 |  | CIP | PLC2 | [8 empty] | °C | 0 | 160
| T1602_TC1002 |  | CIP | PLC2 | [8 empty] | °C | 0 | 160
| T1603_TC1002 |  | CIP | PLC2 | [8 empty] | °C | 0 | 160
Note on B3: Valve number from P&ID

## AO
|  |  | (InTouch) | (InTouch) | [7 empty] | (InTouch) | (InTouch) | (InTouch)
Drawing | ID | Description | Alarm Group | PLC | Impl. PLC | Impl. HMI | Activation | Man mode | Alarm | IO Check | Responsible | Eng. Unit | Eng. Min | Eng. Max
| 9 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0% | 0% | 0% | 0% | 0% | 0% |  |  | Min | Max
| TL0T01M01SC | Tank agitator | TankToTank | PLC1 | [7 empty] | % | 0 | 100
| TL0T02M01SC | Tank agitator | TankToTank | PLC1 | [7 empty] | % | 0 | 100
| TL0L01M01SC | Line pump | TankToTank | PLC1 | [7 empty] | % | 0 | 100
| A50T01M01SC | Tank agitator | TankToTank | PLC1 | [7 empty] | % | 0 | 100
| A50T02M01SC | Tank agitator | TankToTank | PLC1 | [7 empty] | % | 0 | 100
| T1602_RV1000 |  | CIP | PLC2 | [7 empty] | % | 0 | 100
| T1603_RV1000 |  | CIP | PLC2 | [7 empty] | % | 0 | 100
| L1601_RV1100 |  | CIP | PLC2 | [7 empty] | % | 0 | 100
| L1601_SC1101 |  | CIP | PLC2 | [7 empty] | % | 0 | 100
Note on B3: Valve number from P&ID

## Sum
|  |  | (InTouch) | (InTouch) | [7 empty] | (InTouch) | (InTouch) | (InTouch) | (InTouch)
Drawing | ID | Description | Alarm Group | PLC | Impl. PLC | Impl. HMI | Activation | Man mode | Alarm | IO Check | Responsible | Eng. Unit | Eng. Min | Eng. Max | Volume Per Pulse
| 6 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0% | 0% | 0% | 0% | 0% | 0% |  |  | Min | Max | Volume Per Pulse
| TL0L01FT01_Sum | Flow totalizer | TankToTank | PLC1 | [7 empty] | l | 0 | 999999 | 10
| A50L01FT01_Sum | Flow totalizer | TankToTank | PLC1 | [7 empty] | l | 0 | 999999 | 10
| TL0L02FT01_Sum | Flow totalizer | TankToTank | PLC1 | [7 empty] | l | 0 | 999999 | 10
| A30L01FT01_Sum | Flow totalizer | TankToTank | PLC1 | [7 empty] | l | 0 | 999999 | 10
| L1601_FT1101_Sum |  | CIP | PLC2 | [7 empty] | l | 0 | 999999 | 10
| L1601_FT1104_Sum |  | CIP | PLC2 | [7 empty] | l | 0 | 999999 | 10
Note on B3: Valve number from P&ID

## Alarm
Projektnummer:
[11 empty] | Projektnamn: | ProgEx T2T Transfer
Drawing | ID | Description | PLC | Impl. PLC | Impl. HMI | Activation | Test | Alarm | Site Test | Acknowledge | Responsible | Delay seconds
| 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | ON
Note on B3: Valve number from P&ID

## Phases
Projektnummer:
[14 empty] | Projektnamn: | ProgEx T2T Transfer
| Added in PLC |  |  |  |  | Added in HMI | Added in HMI | Added in HMI | Added in HMI | Added in HMI | Office Test | Office Test | Office Test | Office Test | Site Test
| Phase | IL/ RF | Activations | Alarm | Step Seq | Tag list | Start/stop | Indication | Que | menue | Func | Alarm | Valve act | IL/RF
XXXXXXX
XXXXXXXXXXX
XXXXXXXXXXX
XXXXXXXXXXX
XXXXXXXXXXX
XXXXXXXXXXX
XXXXXXXXXXX
XXXXXXX
XXXXXXXXXXX
XXXXXXXXXXX
XXXXXXXXXXX
XXXXXXXXXXX
XXXXXXXXXXX
XXXXXXXXXXX